## Title
The ENS Replacement Project
Work Breakdown Structure and Requirements Traceability Matrix
2022-11-21
Team Members
Keerthana Peri (Z1947534)
Ritika Panthula (Z1948682)

## WBS Dictionary
Project Name: | The ENS Replacement Project
WBS Level | WBS Code | WBS Name | WBS Description | Resources | Due Date | Days
1 | 1 | Initiation | At this stage the project is initiated | Ritika | 2023-01-01 | 1
2 | 1.1 | Project Charter | This charter talks about the risks, constraints, assumptions, and business needs. | Ritika | 2023-01-02 | 1
2 | 1.2 | Project Workability | The project manager analyzes the project needs and gets them approved. | Ritika | 2023-01-03 | 1
3 | 1.2.1 | Evaluations & Recommendations | The Project Charted is evaluated and Recommendations are taken into consideration. | Ritika | 2023-01-04 | 1
3 | 1.2.2 | Project Charter Approvals | After all the changes are done the project charter is sent for approval. | Ritika | 2023-01-05 | 1
1 | 2 | Planning | The stage in which the project flow is decided. | Ritika | 2023-01-06 | 3
2 | 2.1 | Scope Statement | The project manager will take care of all the project outcomes. | Ritika | 2023-01-13 | 7
3 | 2.1.1 | Project Team | The Team that will work on the project is finalized. | Ritika | 2023-01-20 | 7
3 | 2.1.2 | Project Plan Development | A plan for executing the project successfully is drafted. | Ritika, Keerthana | 2023-01-30 | 10
4 | 2.1.2.1 | Project Plan Approvals | The project plan is sent for approval. | Ritika | 2023-02-02 | 3
3 | 2.1.3 | Procure Hardware / Software | All the hardware equipment or the software required for the project is obtained. | Ritika, Keerthana | 2023-02-05 | 6
1 | 3 | Execution | Steps to initiate the project are started. | Ritika, Keerthana | 2023-02-11 | 3
2 | 3.1 | Website Development | Building a user-friendly website and maintaining it in accordance with customer needs. | Ritika, Keerthana | 2023-02-14 | 15
3 | 3.1.1 | Design System | A website needs to be designed. | Ritika, Keerthana | 2023-03-01 | 10
4 | 3.1.1.1 | Install Live System | A live website system needs to be developed. | Ritika, Keerthana | 2023-03-11 | 15
4 | 3.1.1.2 | Verify & Validate User Requirements | All the data about the people that will be using the system needs to be updated. | Keerthana | 2023-03-26 | 12
4 | 3.1.1.3 | End-to-End Testing | The website designed needs to be tested before going live. | Ritika, Keerthana | 2023-04-08 | 27
4 | 3.1.1.4 | User Training | All the people who will be using the system need to be trained. | Ritika, Keerthana | 2023-05-05 | 12
2 | 3.2 | Customer Service | A help section needs to be created for usage in case of any help is required. | Ritika, Keerthana | 2023-05-21 | 15
| 3.2.1 | Go Live | The website will be launched and will be available for people to use it. | Ritika, Keerthana | 2022-05-24 | 3
1 | 4 | Monitoring / Control | The website that is used needs to be monitored. | Ritika | 2023-08-07 | 2
2 | 4.1 | Project Management | The existing project needs to be monitored frequently to manage the project effictively. | Ritika, Keerthana | 2023-08-15 | 2
2 | 4.2 | Risk Management | Risks faced due to the project need to be handles and be taken care of. | Ritika | 2023-08-27 | 2
2 | 4.3 | Updateing Project Management Plan | After monitoring the project progress and its requirements, changes are made to the plan and the structure is updated. | Ritika |  | 2
1 | 5 | Closing | All the project management tasks are closed after successfully completing them. | Ritika, Keerthana | 2023-08-30 | 1
2 | 5.1 | Web Design | Developing a user-friendly website and maintaining it as needed. | Ritika, Keerthana | 2023-09-05 | 1
2 | 5.2 | Audit Procurement | Update about everything related to the project and adding feedback to the audit. | Ritika, Keerthana | 2023-09-15 | 2
2 | 5.3 | Update Files / Records | All the data regarding the project is updated into the system / website. | Ritika, Keerthana | 2023-09-27 | 1

## RTM
Req ID | Requirement description | Source/Requestor | Business justification | WBS deliverable | Test strategy | Status
1 | Infrastructure | Venkata Sidhartha.B | To store both the equipment and food products. | 2.1.3, 2.1.3.1, 2.1.3.2 | Utlizations | Done
2 | Equipment | Venkata Sidhartha.B | To start and get the business running. | 2.1.4 | combination and starting procedure | Done
3 | Manpower | Srikruthi | Manpower for the cooking process, customer service, and app development. | 2.1.5 | Testing their capabilities via screening process. | Inprogress
4 | Food testing | Srikruthi, Reethika | The food testing lab is an integral part of this business system used to test the food products. | 2.1.3.3 | Tested in a labaratory | Inprogress
5 | Appilcation developments | Srikruthi, Reethika | users need to know how to use apps | 3.1, 3.1.1 | End to end testing | Inprogress
6 | Website Development | Srikruthi, Reethika | User-friendly website. | 3.2 | End to end testing | Inprogress
7 | Customer service | Reethika | To help customers in a crisis situation. | 3.3 | By testing and finding out the most efficient tool | Done

## Project Risk Register
S NO. | Risk Description | Justification | Impact Level | Risk Severity | Potential Strategy
1 | Budget Risk | Budget risk needs to be addressed immediately or the business could experience financial troubles. | 5 | Catastrophic | External resources include borrowing money from a bank or a venture capitalist and adhering to rigorous spending plans.
2 | System Crash | Crashing of system causes temporary halts in business operations | 3 | Moderate | employing a qualified software engineer
3 | No show, no work of employee | The business will suffer losses as a result of underperforming staff. | 4 | Moderate | Utilizing competent and experienced labor to prevent these problems and enact the necessary stringent measures if the employee doesn't comply.
4 | Security threats | Issues like security threats is very crucial, malicious users can read you file or software | 5 | Critical | Using security tags to secure the data and also hire professional hacker.
5 | Complexity | The operations being complex is a big risk for the business | 4 | Catastrophic | Using the cloud solutions to reduce the complexity and make it available to every student.
Impact Level
1- Low- Light Green
2- Average- Green
3- Medium- Yellow
4- High- Orange
5- Very High- Red